## Light
PROJECT TITLE
Tian Group |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead | Carl and Gurpreet
Project Start Date: | 2023-03-15 |  |  |  |  | March | [20 empty] | April | [27 empty] | May
Scrolling Increment: | 0 | time axis 2023-03-15 to 2023-05-09
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2023-03-15 to 2023-05-09
Iteration 1
To complete iteration 1 with many requirements achieved | Goal | Carl and Gurpreet | 100% | 2023-03-15 | 4 | 2023-03-15: 2; 2023-03-16: 2; 2023-03-17: 2; 2023-03-18: 2
Stakeholder register and planning | High Risk | Carl | 100% | 2023-03-27 | 5
Repository Git | Low Risk | Gurpreet | 100% | 2023-04-05 | 10
Complete Persona | Med Risk | Carl and Gurpreet | 100% | 2023-04-10 | 5
Iteration 1 completed | Milestone | Carl and Gurpreet | 100% | 2023-04-17 | 1 | bar: 2023-04-17
Iteration 2
To complete iteration 2 with many requirements achieved | Goal | Gurpreet and Carl | 100% | 2023-04-17 | 4 | 2023-04-17: 2; 2023-04-18: 2; 2023-04-19: 2; 2023-04-20: 2
Gantt Chart | High Risk | Gurpreet and Carl | 100% | 2023-04-21 | 5
Resource Needs and Planning | Med Risk | Gurpreet | 100% | 2023-04-26 | 3
Github | Low Risk | Carl | 100% | 2023-05-01 | 2
Iteration 2 Completed | Milestone | Gurpreet and Carl | 100% | 2023-05-01 | 1 | bar: 2023-05-01
Iteration 3
To complete iteration 3 with many requirements achieved | Goal | Gurpreet and Carl | 100% | 2023-05-03 | 4 | 2023-05-03: 2; 2023-05-04: 2; 2023-05-05: 2; 2023-05-06: 2
Risk Register | Med Risk | Gurpreet and Carl | 100% | 2023-05-08 | 3
UAT | Low Risk | Carl | 100% | 2023-05-10 | 4
Final Github | High Risk | Gurpreet | 100% | 2023-05-15 | 5
Iteration 3 completed | Milestone | Gurpreet and Carl | 100% | 2023-05-17 | 1
To add more data, Insert new rows ABOVE this one